## CIP Summary
State of Montana – Long-Range Building Program
6-Year Capital Improvement Plan
Agency: | Dept. of Administration
Prepared by: | Steve Faherty
Date of Plan: | 2025-10-07
Plan Summary (Total Estimated Costs by Year)
Plan Year | Session | Major Repair | Capital Development | Total
Year 1 | 70th (2027-2028) | 2174000 | 3000000 | 5174000
Year 2 | 70th (2027-2028) | 2940000 | 0 | 2940000
Year 3 | 71st (2029-2030) | 5550000 | 0 | 5550000
Year 4 | 71st (2029-2030) | 2425000 | 3500000 | 5925000
Year 5 | 72nd (2031-2032) | 4150000 | 0 | 4150000
Year 6 | 72nd (2031-2032) | 3925000 | 0 | 3925000
Total Request |  | 21164000 | 6500000 | 27664000

## Project Entry
Plan Year | Project Location / Campus | Building Name | Project Title | Project Description | Agency Priority | Estimated Cost | Estimate Cost Year | Estimate Source | Project Type | Project Category | Project Criticality | LRBP Category
1 | Capitol Complex | Capitol Building | Interior Lighting Restoration | Restore and modernize the historic Capitol’s interior lighting to improve efficiency and maintain preservation standards. | 1 | 125000 | 2024 | GSD Estimate | Deferred Maintenance | 2. Damage / Wear-out | Class 2 – Required (Renewal) | Major Repair
1 | Capitol Complex | Walt Sullivan Building | Boiler & Chiller Replacement | Replace aging mechanical systems to ensure heating and cooling reliability throughout the building. | 2 | 474000 | 2024 | GSD Estimate | Deferred Maintenance | 2. Damage / Wear-out | Class 2 – Required (Renewal) | Major Repair
1 | Capitol Complex | Cogswell Building | 0 | Replace outdated elevator systems to meet safety and reliability standards. | 3 | 950000 | 2024 | GSD Estimate | Renovation / Modernization | 2. Damage / Wear-out | Class 3 – Strategic | Major Repair
1 | Capitol Complex | Capitol Complex | Restroom Renovations – Multiple Buildings | Renovate restrooms across Capitol Complex buildings to meet ADA accessibility and modern design standards. | 5 | 625000 | 2024 | GSD Estimate | Renovation / Modernization | 3. Codes / Compliance / Standards | Class 3 – Strategic | Major Repair
1 | Capitol Complex | State Capitol Campus | Underground Utility Repairs – Phase I | Replace deteriorating underground utilities including steam, water, and electrical lines within the Capitol Complex. | 4 | 3000000 | 2024 | GSD Estimate | Infrastructure / Utilities | 2. Damage / Wear-out | Class 2 – Required (Renewal) | Capital Development
2 | Capitol Complex | Mitchell Building | Exterior Envelope Repairs | Repair building envelope, seal leaks, and restore windows to maintain energy efficiency and prevent moisture damage. | 1 | 800000 | 2024 | GSD Estimate | Deferred Maintenance | 2. Damage / Wear-out | Class 2 – Required (Renewal) | Major Repair
2 | Helena | Motor Pool Facility | Roof Replacement | Replace the aging roof system to prevent water infiltration and extend building life. | 2 | 340000 | 2024 | GSD Estimate | Deferred Maintenance | 2. Damage / Wear-out | Class 1 – Critical | Major Repair
2 | Capitol Complex | Old Livestock Building | Mechanical System Replacement | Replace outdated mechanical systems to improve efficiency and indoor comfort. | 4 | 1200000 | 2024 | Consultant Estimate | Renovation / Modernization | 4. Energy & Operational Efficiency | Class 3 – Strategic | Major Repair
2 | Capitol Complex | 125 N. Roberts | Window and Door Replacements | Replace windows and exterior doors to improve building envelope performance and reduce energy costs. | 3 | 600000 | 2024 | GSD Estimate | Deferred Maintenance | 2. Damage / Wear-out | Class 3 – Strategic | Major Repair
3 | Capitol Complex | Cogswell Building | Fire Alarm & Sprinkler Upgrades | Upgrade fire alarm and sprinkler systems to meet current life safety codes. | 1 | 750000 | 2025 | GSD Estimate | Renovation / Modernization | 3. Codes / Compliance / Standards | Class 3 – Strategic | Major Repair
3 | Capitol Complex | State Library Building | HVAC System Replacement | Replace the aging HVAC system for improved efficiency and comfort in library facilities. | 2 | 1450000 | 2025 | GSD Estimate | Deferred Maintenance | 4. Energy & Operational Efficiency | Class 3 – Strategic | Major Repair
3 | Capitol Complex | State Data Center | Electrical Distribution Upgrade | Upgrade electrical distribution for increased capacity and reliability in the data center. | 3 | 950000 | 2025 | GSD Estimate | Infrastructure / Utilities | 4. Energy & Operational Efficiency | Class 3 – Strategic | Major Repair
3 | Capitol Complex | Old Board of Health Building | Interior Renovation | Renovate interior spaces for modern standards and improved office functionality. | 4 | 2400000 | 2025 | Consultant Estimate | Renovation / Modernization | 5. Renovation & Enhancements | Class 3 – Strategic | Major Repair
4 | Capitol Complex | State Capitol Campus | Campus Infrastructure Modernization – Phase III | Modernize HVAC, electrical, and water systems as part of ongoing infrastructure renewal. | 4 | 3500000 | 2025 | GSD Estimate | Infrastructure / Utilities | 5. Renovation & Enhancements | Class 3 – Strategic | Capital Development
4 | Capitol Complex | Scott Hart Building | Roof and Masonry Repairs | Repair roof and restore exterior masonry to prevent water infiltration. | 1 | 875000 | 2025 | GSD Estimate | Deferred Maintenance | 2. Damage / Wear-out | Class 1 – Critical | Major Repair
4 | Capitol Complex | State Print & Mail Facility | HVAC Replacement | Replace HVAC system to improve efficiency and maintain consistent temperature and humidity for printing operations. | 3 | 650000 | 2025 | GSD Estimate | Deferred Maintenance | 4. Energy & Operational Efficiency | Class 2 – Required (Renewal) | Major Repair
4 | Capitol Complex | Motor Pool Facility | Fuel System Modernization | Upgrade fueling systems for safety, compliance, and monitoring accuracy. | 2 | 525000 | 2025 | GSD Estimate | Infrastructure / Utilities | 3. Codes / Compliance / Standards | Class 3 – Strategic | Major Repair
4 | Capitol Complex | State Capitol Building | Restoration of Public Entrances | Restore exterior stonework and doors at Capitol entrances to maintain historic integrity. | 5 | 375000 | 2025 | GSD Estimate | Renovation / Modernization | 5. Renovation & Enhancements | Class 3 – Strategic | Major Repair
5 | Capitol Complex | Walt Sullivan Building | Exterior Envelope Renewal | Renew the exterior cladding and insulation for improved performance and reduced maintenance costs. | 3 | 1100000 | 2026 | GSD Estimate | Deferred Maintenance | 5. Renovation & Enhancements | Class 3 – Strategic | Major Repair
5 | Helena | State Data Center | Generator and UPS Replacement | Replace end-of-life emergency power and UPS systems to ensure continued data reliability. | 1 | 850000 | 2026 | Consultant Estimate | Infrastructure / Utilities | 2. Damage / Wear-out | Class 1 – Critical | Major Repair
5 | Capitol Complex | 125 N. Roberts | Interior Renovation and Office Reconfiguration | Reconfigure offices to support agency modernization and improved efficiency. | 4 | 1750000 | 2026 | GSD Estimate | Renovation / Modernization | 5. Renovation & Enhancements | Class 2 – Required (Renewal) | Major Repair
5 | Capitol Complex | State Library Building | Lighting and Controls Upgrade | Upgrade lighting and control systems for energy efficiency and occupant comfort. | 2 | 450000 | 2026 | GSD Estimate | Deferred Maintenance | 4. Energy & Operational Efficiency | Class 2 – Required (Renewal) | Major Repair
6 | Capitol Complex | Capitol Building | Roof Replacement | Replace the Capitol roof to protect the building and preserve its historic character. | 1 | 1650000 | 2026 | GSD Estimate | Deferred Maintenance | 2. Damage / Wear-out | Class 2 – Required (Renewal) | Major Repair
6 | Capitol Complex | Scott Hart Building | Elevator Modernization | Modernize elevator systems to improve accessibility, safety, and reliability. | 2 | 900000 | 2026 | GSD Estimate | Renovation / Modernization | 2. Damage / Wear-out | Class 2 – Required (Renewal) | Major Repair
6 | Helena | State Print & Mail Facility | Building Systems Modernization | Upgrade building systems to extend service life and improve energy efficiency. | 4 | 775000 | 2026 | GSD Estimate | Renovation / Modernization | 2. Damage / Wear-out | Class 2 – Required (Renewal) | Major Repair
6 | Capitol Complex | 125 N. Roberts | Exterior Envelope Rehabilitation | Repair façade, replace sealants, and improve water barrier integrity. | 3 | 600000 | 2026 | GSD Estimate | Deferred Maintenance | 2. Damage / Wear-out | Class 2 – Required (Renewal) | Major Repair

## Session Summary
Project Location / Campus | (All)
Sum of Estimated Cost
|  | Year 1 |  | Year 1 Total | Year 2 | Year 2 Total | Year 3 | Year 3 Total | Year 4 |  | Year 4 Total | Year 5 | Year 6 | Grand Total
|  | Capital Development | Major Repair |  | Major Repair |  | Major Repair |  | Capital Development | Major Repair
Capitol Building | Roof Replacement | [11 empty] | 1650000 | 1650000
| Interior Lighting Restoration |  | 125000 | 125000 | [9 empty] | 125000
Capitol Building Total |  |  | 125000 | 125000 | [8 empty] | 1650000 | 1775000
Mitchell Building | Exterior Envelope Repairs |  |  |  | 800000 | 800000 | [7 empty] | 800000
Mitchell Building Total |  |  |  |  | 800000 | 800000 | [7 empty] | 800000
Scott Hart Building | Elevator Modernization | [11 empty] | 900000 | 900000
| Roof and Masonry Repairs | [8 empty] | 875000 | 875000 |  |  | 875000
Scott Hart Building Total | [9 empty] | 875000 | 875000 |  | 900000 | 1775000
Capitol Complex | Restroom Renovations – Multiple Buildings |  | 625000 | 625000 | [9 empty] | 625000
Capitol Complex Total |  |  | 625000 | 625000 | [9 empty] | 625000
Walt Sullivan Building | Boiler & Chiller Replacement |  | 474000 | 474000 | [9 empty] | 474000
| Exterior Envelope Renewal | [10 empty] | 1100000 |  | 1100000
Walt Sullivan Building Total |  |  | 474000 | 474000 | [7 empty] | 1100000 |  | 1574000
Cogswell Building | Elevator Modernization |  | 950000 | 950000 | [9 empty] | 950000
| Fire Alarm & Sprinkler Upgrades | [5 empty] | 750000 | 750000 | [5 empty] | 750000
Cogswell Building Total |  |  | 950000 | 950000 |  |  | 750000 | 750000 | [5 empty] | 1700000
State Capitol Campus | Underground Utility Repairs – Phase I | 3000000 |  | 3000000 | [9 empty] | 3000000
| Campus Infrastructure Modernization – Phase III | [7 empty] | 3500000 |  | 3500000 |  |  | 3500000
State Capitol Campus Total |  | 3000000 |  | 3000000 |  |  |  |  | 3500000 |  | 3500000 |  |  | 6500000
Motor Pool Facility | Roof Replacement |  |  |  | 340000 | 340000 | [7 empty] | 340000
| Fuel System Modernization | [8 empty] | 525000 | 525000 |  |  | 525000
Motor Pool Facility Total |  |  |  |  | 340000 | 340000 |  |  |  | 525000 | 525000 |  |  | 865000
Old Livestock Building | Mechanical System Replacement |  |  |  | 1200000 | 1200000 | [7 empty] | 1200000
Old Livestock Building Total |  |  |  |  | 1200000 | 1200000 | [7 empty] | 1200000
125 N. Roberts | Window and Door Replacements |  |  |  | 600000 | 600000 | [7 empty] | 600000
| Interior Renovation and Office Reconfiguration | [10 empty] | 1750000 |  | 1750000
| Exterior Envelope Rehabilitation | [11 empty] | 600000 | 600000
125 N. Roberts Total |  |  |  |  | 600000 | 600000 | [5 empty] | 1750000 | 600000 | 2950000
State Library Building | HVAC System Replacement | [5 empty] | 1450000 | 1450000 | [5 empty] | 1450000
| Lighting and Controls Upgrade | [10 empty] | 450000 |  | 450000
State Library Building Total | [6 empty] | 1450000 | 1450000 |  |  |  | 450000 |  | 1900000
Old Board of Health Building | Interior Renovation | [5 empty] | 2400000 | 2400000 | [5 empty] | 2400000
Old Board of Health Building Total | [6 empty] | 2400000 | 2400000 | [5 empty] | 2400000
State Data Center | Electrical Distribution Upgrade | [5 empty] | 950000 | 950000 | [5 empty] | 950000
| Generator and UPS Replacement | [10 empty] | 850000 |  | 850000
State Data Center Total | [6 empty] | 950000 | 950000 |  |  |  | 850000 |  | 1800000
State Print & Mail Facility | HVAC Replacement | [8 empty] | 650000 | 650000 |  |  | 650000
| Building Systems Modernization | [11 empty] | 775000 | 775000
State Print & Mail Facility Total | [9 empty] | 650000 | 650000 |  | 775000 | 1425000
State Capitol Building | Restoration of Public Entrances | [8 empty] | 375000 | 375000 |  |  | 375000
State Capitol Building Total | [9 empty] | 375000 | 375000 |  |  | 375000
Grand Total |  | 3000000 | 2174000 | 5174000 | 2940000 | 2940000 | 5550000 | 5550000 | 3500000 | 2425000 | 5925000 | 4150000 | 3925000 | 27664000

## Agency Priority
Project Location / Campus | (All)
Projects by Category | Agency Project Priority
1
2. Damage / Wear-out
Interior Lighting Restoration | 1
Boiler & Chiller Replacement | 2
Elevator Modernization | 3
Underground Utility Repairs – Phase I | 4
3. Codes / Compliance / Standards
Restroom Renovations – Multiple Buildings | 5
2
2. Damage / Wear-out
Exterior Envelope Repairs | 1
Roof Replacement | 2
Window and Door Replacements | 3
4. Energy & Operational Efficiency
Mechanical System Replacement | 4
3
3. Codes / Compliance / Standards
Fire Alarm & Sprinkler Upgrades | 1
4. Energy & Operational Efficiency
HVAC System Replacement | 2
Electrical Distribution Upgrade | 3
5. Renovation & Enhancements
Interior Renovation | 4
4
2. Damage / Wear-out
Roof and Masonry Repairs | 1
3. Codes / Compliance / Standards
Fuel System Modernization | 2
4. Energy & Operational Efficiency
HVAC Replacement | 3
5. Renovation & Enhancements
Campus Infrastructure Modernization – Phase III | 4
Restoration of Public Entrances | 5
5
2. Damage / Wear-out
Generator and UPS Replacement | 1
4. Energy & Operational Efficiency
Lighting and Controls Upgrade | 2
5. Renovation & Enhancements
Exterior Envelope Renewal | 3
Interior Renovation and Office Reconfiguration | 4
6
2. Damage / Wear-out
Roof Replacement | 1
Elevator Modernization | 2
Exterior Envelope Rehabilitation | 3
Building Systems Modernization | 4