## Instructions
#VALUE!
Instructions for Project Timeline tab
Required | Populate the "Project Timeline - All Phases" table (rows 10-17). For each program milestone, enter in the starting month (cells E10 to E17) and milestone duration (F10 to F17). The project start (the beginning of Month 1) occurs when an awarded subgrantee receives its subgrantee award from Connect MT; the start of each individual milestone must be provided in relation to the project start. Milestone durations must be provided in units of months and are not to be tied to specific calendar dates. Responses should only be integers ranging from 1 to 48. Input the project's total number of BSLs in cell C8 and the total number of miles in cell D8. The percentages (cell C9, D9) will automatically calculate. If the project does not include any new miles, input "0" (zero) in cell D8 - do not leave it blank. The Network Activation & Program Closeout milestone represents the month in which the subgrantee proposes to complete the project by submitting the required closeout materials. Per BEAD Program requirements, the project timeline may not extend beyond the four year timeframe (48 months). The milestones must only encompass BEAD-funded deployment activities. Items such as ongoing subscriber activations (post-program) and ongoing maintenance should not be included in the timeline.
Conditionally required | If the project includes phasing, provide phase-specific milestone timelines. This is in addition to populating the "All Phases" table (row 10-17). If the project includes multiple phases, copy the table in rows 20-27 and paste as many times as needed, and indicate the correct phase number. For each phase, provide the number of BSLs to be connected and miles to be deployed. Note: there are three milestones that only occur once and they are listed in the "All Phases" table - Project Planning, Environmental and Historic Preservation (EHP), and Project Closeout.
Instructions for Reimbursement Schedule tab
Required | Provide the estimated disbursement submission month for each milestone by populating the table (Cells C10 to C35). Only populate the non-grey cells with an integer ranging from 1 to 48. Do not edit any other part of the templated tab.

## Project Info
#VALUE!
Project Information
Subgrantee name
Project name
Project Award/ID
Awarding Authority | ConnectMT
Program Name | BEAD
Date Submitted

## Project Timeline
#VALUE!
Project Timeline - All Project Phases
Duration
Project Timeline - All Phases | Project BSLs | Project Miles | Start (Month) | Duration (Months)
[5 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
| #DIV/0! | #DIV/0! |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Planning |  |  | 1 | 1
Design Engineering |  |  | 1 | 1
Environmental and Historic Preservation (EHP) |  |  | 1 | 1
Engineering and Permitting Approvals |  |  | 1 | 1
Materials Acquisition |  |  | 1 | 1
Deployment |  |  | 1 | 1
Network Activation & Testing |  |  | 1 | 1
Project Closeout |  |  | 1 | 1
Project Timeline - Phase 1 | Phase BSLs | Phase Miles | Start (Month) | Duration (Months) | bar: Year 1 1 to Year 4 48
[5 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
| #DIV/0! | #DIV/0! |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
Design Engineering |  |  | 1 | 1
Engineering and Permitting Approvals |  |  | 1 | 1
Materials Acquisition |  |  | 1 | 1
Deployment |  |  | 1 | 1
Network Activation & Testing |  |  | 1 | 1
[Copy Rows Above for Each Proposed Project Phase]

## Disbursement Schedule
#VALUE!
Anticipated Milestone Disbursement Schedule
Anticipated Milestone Submission Date Month
| Program Milestone | Estimated Submission Month
|  |  |  | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Project Planning |  | 1
| Aggregated project plan with milestones and budget. |  | 1
| Engineering & Permitting |  | 1
| Completed engineering drawings and executed permits for 20% of project BSLs. |  | 1
| Completed engineering drawings and executed permits for 40% of project BSLs. |  | 1
Completed engineering drawings and executed permits for 60% of project BSLs.
Completed engineering drawings and executed permits for 80% of project BSLs.
| Completed engineering drawings and executed permits for 100% of project BSLs. |  | 1
| Pre-Deployment |  | 1
| Documentation of binding agreements for required contracted labor and materials. Evidence of construction staging and material delivery for 20% of project BSLs. |  | 1
| Documentation of binding agreements for required contracted labor and materials. Evidence of construction staging and material delivery for 40% of project BSLs. |  | 1
Documentation of binding agreements for required contracted labor and materials. Evidence of construction staging and material delivery for 60% of project BSLs.
Documentation of binding agreements for required contracted labor and materials. Evidence of construction staging and material delivery for 80% of project BSLs.
| Documentation of binding agreements for required contracted labor and materials. Evidence of construction staging and material delivery for 100% of project BSLs. |  | 1
| Deployment |  | 1
| Completed placement of broadband infrastructure and associated as-built documentation for 20% of project BSLs. |  | 1
| Completed placement of broadband infrastructure and associated as-built documentation for 40% of project BSLs. |  | 1
Completed placement of broadband infrastructure and associated as-built documentation for 60% of project BSLs.
Completed placement of broadband infrastructure and associated as-built documentation for 80% of project BSLs.
| Completed placement of broadband infrastructure and associated as-built documentation for 100% of project BSLs. |  | 1
| Network Activation & Program Closeout |  | 1
| Completed network activation and submission of subscriber test data for 20% of project BSLs. |  | 1
| Completed network activation and submission of subscriber test data for 40% of project BSLs. |  | 1
Completed network activation and submission of subscriber test data for 60% of project BSLs.
Completed network activation and submission of subscriber test data for 80% of project BSLs.
| Completed network activation and submission of subscriber test data for 100% of project BSLs. Completion of all program closeout requirements. |  | 1